Harmonized Multi-Model CONUS Forest Assessment

Status brief for project continuity and coauthor circulation

Prepared 2026-06-09  ·  CRSF / OSC Cardinal (PUOM0008)  ·  repo github.com/holoros/landis2HPC

# Bottom line

Two models are CONUS-complete (FVS and the yield curves). LANDIS-II is complete for four states and stuck on Wisconsin and Michigan for a reason the last fix did not address. CEM and CBM are not yet on the common pipeline. The headline cross-model result exists, but only as LANDIS versus FVS on four states. The critical path runs through the LANDIS WI/MI failure.

# Model coverage at a glance

| Model | CONUS coverage | Harmonized-pipeline status |
| --- | --- | --- |
| FVS | 48 states | Resolved. Common harvest, FIA-anchored. harmonized_fvs_carbon_npv.csv. |
| Yield curves | 48 states | CONUS-complete with rcp45/85 + FIADB/TreeMap. Still on native harvest; needs re-anchor to share harvest axis. |
| LANDIS-II | 4 of target states | WA, MN, OH, IN carry full multi-criteria vectors. WI/MI broken; ME/GA not built. |
| CEM | Extending | cem_rerun array active on Cardinal. Not yet on common per-plot per-ha pipeline. |
| CBM | FIA-native | No movement. Per-plot per-ha adapter still pending. |

Green = ready for the common pipeline; amber = partial; red = blocked.

# LANDIS-II per-state status (live from Cardinal)

Trajectory counts verified directly in /fs/scratch/PUOM0008/crsfaaron/landis2/states/<ST>/perseus/statewide/ on 2026-06-09. “With real data” counts only trajectories containing a data row beyond the header.

| State | Trajectories | With real data | Status |
| --- | --- | --- | --- |
| WA | 1,355 | 1,355 | Complete |
| MN | 1,148 | 1,148 | Complete |
| OH | 178 | 178 | Complete |
| IN | 214 | 212 | Effectively complete |
| WI | 636 | 2 | Broken (empty stubs) |
| MI | 401 | 0 | Broken (empty stubs) |
| ME | none | – | Not built |
| GA | none | – | Build running (ga_conus_hm2) |

## Why WI and MI are still broken

The 2026-06-08 handoff recorded that the IC-filter and wall-time fixes were applied and the runs were “finishing.” The live check shows they did not. WI has 2 of 636 plots with data; MI has 0 of 401. The Michigan resubmit (swMI, job 11401259) shows every array task completing in roughly 15 seconds with empty .out and .err files and header-only trajectory stubs (a biomass_trajectory.csv that contains only the column header line).

That signature means the harness writes the CSV header and exits before LANDIS actually runs, so the per-task wall-time increase could not have been the real cause. The skip check also lets these zero-data stubs count as present. The likely culprits are the IC-filter excluding all MI/WI plots, or the per-plot build step failing fast while the task still exits 0. The fix needs to target the build-to-run handoff, not the wall clock.

# Cross-model result to date

Holds as reported. Both models are anchored to the same FIA year-0, so the 2100 divergence is pure model structure: roughly 2x disagreement, direction flipping by region (LANDIS higher in the East and Lake States, FVS far higher in the Pacific Northwest), scenario ordering reserve > conservation > BAU > intensive preserved in both. 2100 total carbon (forest + HWP), LANDIS vs FVS: IN 565 vs 313, MN 838 vs 387, OH 768 vs 511, WA 1,371 vs 2,272 Tg C.

# Active Cardinal jobs (2026-06-09)

- cem_rerun – CEM CONUS extension array, 13 tasks running, hitting the array task limit.

- ga_conus_hm2 – Georgia harmonized build, ~13.5 h elapsed.

- lsog_phase10 – LSOG metric work.

- Plus unrelated runs: compos_v2_prod, cspi_v5_stage1, ql_s10, stress_mort.

# Data flag worth confirming

The report cites the keystone configuration at cbm_states/cross_state/libcbm/tools_conus. On Cardinal, cbm_states/ contains only states/{IN,GA,OR}; the cross_state/libcbm/tools_conus path was not found. Either the harmonized config lives elsewhere now or the reference is stale. Confirm before CEM/CBM harmonization depends on it.

# Recommended next steps, in priority order

- Fix the WI/MI LANDIS runs (critical path). Diagnose the ~15-second empty-stub completion in the build-to-run handoff; this unblocks the six-state harvest table.

- Re-anchor the yield curves. Re-anchor to the FIA design value and re-run from the reserve trajectory under the common harvest, making a three-model (FVS, yield curve, LANDIS) comparison strictly valid on the harvest axis.

- Build ME and GA statewide LANDIS runs (GA build already in flight).

- Bring CEM, then CBM, onto the common pipeline via the per-plot per-ha adapter, toward the five-model multi-criteria tradeoff frontier.

- Replace synthetic stumpage ($14/m3 placeholder) with real regional series and regenerate the economics.

Sources: Harmonized_MultiModel_Assessment_Report.docx; landis2HPC/docs/SESSION_HANDOFF_2026-06-08_FULL.md; live Cardinal queue, scratch, and run-directory inspection (PUOM0008), 2026-06-09.