# Harmonized Multi-Model, Multi-Scenario CONUS Forest Assessment

Plan, status, methods, and cross-model results for the apples-to-apples LANDIS / FVS / yield-curve / CEM / CBM comparison.

Prepared 2026-06-08 for project continuity (CRSF / OSC Cardinal, project PUOM0008). This document gives a future session the full context needed to resume the work.

# 1. Purpose and framing

The goal is an apples-to-apples comparison of forest-carbon and ecosystem-service projections across multiple models (LANDIS-II, FVS, empirical yield curves, CEM, CBM), following the Daigneault et al. (2024) multi-model framing. Every model consumes the same inputs so that differences in projected outcomes are attributable to model structure, not to setup. The keystone configuration is harmonized_scenarios.yml in cbm_states/cross_state/libcbm/tools_conus.

Locked common elements: CONUS lower 48; horizon 2025 to 2100 (5-year steps); a single carbon fraction (0.5); current climate as the headline with rcp45/85 as a sensitivity; forest area from FIA EXPNS; one harvest driver (HCS per-state rate); and a common FIA year-0 anchor that rescales every model to the same starting stock, isolating dynamics.

# 2. Architecture

- Single spatial substrate: TreeMap. Models run per FIA plot; TreeMap's plot-to-pixel imputation provides spatial allocation. The state-level result uses plot-mean per-ha carbon anchored to the FIA total (painting reserved for sub-state maps).

- FIA anchor: each model is rescaled so its year-0 (2025) total equals the FIA design-based estimate per state; only the post-2025 dynamics differ between models.

- Common harvest: the HCS per-state annual harvest rate, scaled by a scenario multiplier, applied as a deterministic expected-value removal flux. This is what keeps harvest identical across models.

- Plot linkage by physical plot identity (STATECD_COUNTYCD_PLOT), not raw control number, because sources carry different inventory-cycle CNs (crosswalk cn2pid.csv, ~2M rows).

# 3. Scenario protocol

Four management scenarios at current climate (Daigneault taxonomy). Climate is a separate, capability-restricted sensitivity layer (not all models represent climate or disturbance, so blending it into the core comparison would let assumptions dominate).

| Scenario | Harvest x | Description / prescription |
| --- | --- | --- |
| reserve | 0.0 | No harvest / set-aside |
| conservation | 0.6 | Extensive partial harvest, longer rotations |
| BAU | 1.0 | Current harvest = HCS per-state rate |
| intensive | 2.0 | Clearcut emphasis (land-sparing intensive) |

# 4. Shared foundations (complete)

- HCS per-state harvest rates, 48 states (harmonized/hcs_harvest_rate_by_state.csv): 0 to 5.19 %/yr, median 0.11; near-zero in the arid West, ~1.4 %/yr in the Southeast.

- FIA design-based year-0 anchor with standard errors, 48 states, EVALIDator-mirroring estimator (fia_design_estimate.R): CONUS 15.28 Pg C live AGC; per-state CV ~1 % (well-forested) to ~7 % (sparse plains).

- TreeMap painter (treemap_paint.R) and the aggregation / anchor-rescale / acceptance layer with SE propagation (harmonized_aggregate.R).

- Scenario + metric engine (apply_harvest_scenarios.R): forest carbon, harvested wood products (HWP) carbon, total carbon, and timber NPV, all from the same harvest removals; LSOG biomass proxy (lsog_proxy.R).

# 5. Model status

| Model | Coverage | Status |
| --- | --- | --- |
| LANDIS-II | WA, MN complete; IN/OH/WI/MI in progress | Per-plot, per-ha anchored, common harvest. Full multi-criteria vector (carbon+HWP, NPV, LSOG) for WA/MN/IN/OH. Per-plot run failures (header-only stubs) fixed; runs finishing. ME/GA need statewide runs built. |
| FVS | 48 states (CONUS) | RESOLVED. Reserve from per-stand densities (out_gompit_v3 conus_*.csv, gompit config), anchored to FIA, common harvest. harmonized_fvs_carbon_npv.csv. |
| Yield curves | 48 states / CONUS | Native 4-scenario carbon with uncertainty bands (conus_aggregated_yields.csv), rcp45/85, FIADB+TreeMap allocations. Reserve harmonizable; native scenarios use the model's own harvest (re-anchor + common harvest needed for strict comparison). |
| CEM | GA/ME/MN/WA, extending | Running on Cardinal (cem_rerun array). Needs per-plot per-ha adapter into the common pipeline. |
| CBM | 48 (FIA-native) | Pending a per-plot per-ha adapter. |

# 6. Cross-model results to date

## 6.1 LANDIS vs FVS, 2100 total carbon (forest + HWP), Tg C

Both anchored to the same FIA year-0, so the 2100 divergence is purely model structure. The models disagree by roughly 2x, and the direction flips by region.

| State | LANDIS reserve | FVS reserve | LANDIS intensive | FVS intensive |
| --- | --- | --- | --- | --- |
| IN | 565 | 313 | 514 | 280 |
| MN | 838 | 387 | 663 | 286 |
| OH | 768 | 511 | 714 | 469 |
| WA | 1371 | 2272 | 1360 | 2255 |

LANDIS accumulates more carbon in the East and Lake States; FVS far more in the Pacific Northwest. Scenario ordering (reserve > conservation > BAU > intensive) holds in both.

## 6.2 CONUS scenario carbon by model, 2100 (Tg C live AGC)

Caveat: FVS uses the common harvest; the yield-curve figures below are the model's native scenarios (own harvest intensity) on its own year-0, so they are not yet strictly comparable on the harvest axis. LANDIS is not yet CONUS-complete.

| Model (basis) | reserve | conservation | BAU | intensive |
| --- | --- | --- | --- | --- |
| FVS (common harvest, FIA anchor) | 32207 | 30154 | 28066 | 25591 |
| Yield curves (native, own y0=11061) | 20815 | 15633 | 9413 | 5688 |

The contrast in harvest sensitivity (FVS reserve-to-intensive -21 % vs yield-curve -73 %) is partly real model difference and partly the harvest-protocol difference (common vs native). Re-running yield curves under the common harvest from their reserve trajectory is the fix.

## 6.3 Updated yield-curve findings (this session)

- All four harmonized scenarios are available at CONUS with uncertainty bands (lo/hi), under rcp45 and rcp85, and under FIADB and TreeMap spatial allocations (ycx_canon).

- CONUS reserve live AGC: 11,061 Tg C (2025) to 20,815 [20,580 to 21,499] (2100); conservation 15,633; BAU 9,413; intensive 5,688.

- Yield-curve year-0 (11,061 Tg C) sits below the FIA design anchor (15,279 Tg C), an empirical-vs-design-estimator gap; harmonization re-anchors to the design value.

- Outputs: conus_aggregated_yields.csv (metric x scenario x year x value/lo/hi), per-state files under yield_curves_conus/.

# 7. Metrics

## 7.1 Carbon: forest + harvested wood products

Total carbon = standing forest AGC + HWP. HWP is a first-order pool: of removed carbon, 50 % enters products, split long-lived (sawnwood/panels, 35-yr half-life) and short-lived (paper, 4-yr), with a landfill pool (100-yr); storage only, no material-substitution credit. HWP recovers ~20 to 25 % of harvest-driven forest carbon loss by 2100.

## 7.2 Economics: NPV / stumpage

Timber NPV is valued from each scenario's own removals at 3 % and 5 % discount, kept on a separate axis from physical carbon. Stumpage is currently a generic placeholder ($14/m3, 2020 USD; merchantable fraction 0.6; 1.9 m3/Mg). Real benchmarks for the refinement: southern pine sawtimber ~$22 to 25/ton, hardwood ~$16 to 35/ton, Pacific Northwest Douglas-fir ~$42 to 55/ton. The ecoregion_npv_by_rate.csv product carries NPV at four discount rates but only populated timber for BAU, so timber-from-removals is used for the cross-scenario comparison.

## 7.3 Ecosystem services

An LSOG biomass-threshold proxy (fraction of plots with live AGC above 75 Mg C/ha) is computed across scenarios now. The rigorous age-based LSOG, plus biodiversity (species richness/diversity) and habitat suitability, require a metrics-output LANDIS rerun that retains cohort age, per-species biomass, and the habitat extensions (a configuration change; the container already has the extensions).

# 8. Methods and key assumptions

| Parameter | Value | Note |
| --- | --- | --- |
| Carbon fraction | 0.5 | Common; CEM internal 0.47 reconciled on output |
| HWP to products | 0.50 | Rest = slash/mill loss |
| HWP half-lives | 35 / 4 / 100 yr | long-lived / short-lived / landfill |
| Removal fraction f | 0.85 clearcut, 0.45 partial | BAU blends by state clearcut fraction |
| Stumpage | $14/m3 (placeholder) | Replace with regional series |
| Discount rate | 3 % and 5 % | headline; 7 %/10 % sensitivity |
| LSOG threshold | 75 Mg C/ha | biomass proxy for late-successional |

# 9. Open decisions

- Monetize carbon in a net NPV, or keep carbon and dollars separate (current: separate, recommended).

- Real regional stumpage source and refit of the stumpage imputation.

- HWP storage-only vs a material-substitution credit.

- LSOG age/structure thresholds and the focal habitat species set.

- Whether to commit the metrics-output LANDIS rerun that unlocks age-based LSOG, biodiversity, and habitat.

# 10. Next steps

- Finish the LANDIS IN/OH/WI/MI runs (stub fix applied) and run the clean six-state harvest; build ME and GA.

- Re-anchor yield curves to the FIA design anchor and apply the common harvest from their reserve trajectory, so all models share the harvest axis.

- Adapt CEM and CBM to the per-plot per-ha schema and bring them onto the common pipeline.

- Replace synthetic stumpage with real regional series; regenerate NPV.

- Commit the metrics-output rerun for the full ecosystem-service suite; assemble the five-model multi-criteria tradeoff frontier.

# 11. File and script inventory

Repo (github.com/holoros/landis2HPC), harmonized/ : fia_design_estimate.R, fia_domain_estimator.R, treemap_paint.R, harmonized_aggregate.R, landis_adapter.R, build_landis_reserve_perha.R, apply_harvest_scenarios.R, lsog_proxy.R, build_fvs_reserve_v2.R; data fia_agc_anchor_design_by_state.csv, hcs_harvest_rate_by_state.csv, harmonized_carbon_npv_4state.csv, harmonized_lsog_proxy_4state.csv, harmonized_fvs_carbon_npv.csv, harmonized_crossmodel_LANDIS_FVS.csv. docs/ : the dated SESSION_HANDOFF files (the FULL one is the master state), treemap_substrate_plan.md, multicriteria_metrics_framework.md, CONUS_rollout_roadmap_v2.0.md.

Cardinal: FIA/ (anchor, estimators, cn2pid.csv, LANDIS adapter outputs); landis2/tools/run_statewide_buildfresh.sh and the per-state build/apply tools; landis2/states/<ST>/perseus/statewide/<tag>/ (LANDIS per-plot runs); fvs_stress/ (FVS densities out_gompit_v3, managed runs, treemap compare); conus_aggregated_yields.csv and yield_curves_conus/ (yield curves); cbm_states/cross_state/libcbm/tools_conus/ (harmonized config, HCS, CEM/CBM).